## About
Declaration of AI Assistance: All data modeling, functions, and analytical logic within these Excel projects were developed independently. Generative AI tools (ChatGPT and Gemini) were utilized solely to enhance syntax, tone, and readability of textual elements.
Construction Project Monitoring Dashboard
A single-project cost, billing and progress dashboard for a construction project at 75% completion.
⚠ ILLUSTRATIVE / SAMPLE DATA — built to demonstrate methodology. Project 'Skyline Terraces — Block C', all names and figures are fictional and do not represent any real company or client.
WHAT THIS SHOWS
• Live KPI tiles: total budget (₹16 Cr), amount spent, % utilised, completion %, cost variance, estimate at completion, and RA billing position.
• Cost breakdown by category (material, labour, subcontractor, equipment, overheads) with a donut chart and cost-to-complete.
• RA Bill status — running-account bills raised to the client: gross value, certified, 5% retention, received and pending.
• Subcontractor tracker — order value, billed, paid and balance by work package.
• Project-specific manpower and work-time costing (headcount × days × rate).
• Material consumption (budget vs actual quantity) and Purchase Price Variance for cement and steel.
• Milestone/schedule tracker (planned vs actual %) and a monthly cash-flow view (inflow vs outflow, cumulative).
• Every figure is formula-driven across seven data tabs — change an input and the dashboard updates.
SKILLS DEMONSTRATED
Project cost control · MIS reporting · Budget vs actual & variance analysis · RA billing & retention · Purchase price variance · Cash-flow tracking · Advanced Excel (cross-sheet formulas, IFERROR, charts) · Management accounting
Built by Akhila Nayak · Accountant · R2R, MIS & Cost Analysis

## Dashboard
Construction Project Monitoring Dashboard
Skyline Terraces — Block C · 75% Complete · ₹16 Cr Estimate · Illustrative data (INR)
TOTAL BUDGET |  | AMOUNT SPENT |  |  | % UTILISED |  | COMPLETION
160000000 |  | 122600000 |  |  | 76.62% |  | 75%
COST VAR (EV−AC) |  | CPI |  |  | EAC (BAC/CPI) |  | RA RECEIVED
-2600000 |  | 0.97879 |  |  | 163466666.6667 |  | 114100000
COST BREAKDOWN BY CATEGORY |  |  | RA BILL SUMMARY |  |  | EARNED VALUE (EVM)
Category | Actual (₹)
Material | 50200000 |  | Gross Work Value | 131500000 |  | BAC — Budget | 160000000
Labour | 30800000 |  | Amount Certified | 128600000 |  | EV — Earned Value | 120000000
Subcontractor | 23100000 |  | Retention Held | 6430000 |  | AC — Actual Cost | 122600000
Equipment | 10600000 |  | Amount Received | 114100000 |  | CPI | 0.97879
Overheads | 7900000 |  | Pending Receivable | 8070000 |  | VAC — Var at Completion | -3466666.6667

## Project_Data
Project Master Data
Project Name | Skyline Terraces — Block C
Project Type | Construction (Residential/Commercial)
Total Estimated Cost (Budget) | 160000000
Overall Completion % | 75%
Planned Completion % (as per schedule) | 80%
Project Start | Apr 2024
Scheduled Completion | Mar 2026
Cost by Category
Category | Budget (₹) | Actual to Date (₹) | % of Budget Spent | Cost to Complete (₹)
Material | 64000000 | 50200000 | 78.44% | 13800000
Labour | 40000000 | 30800000 | 77% | 9200000
Subcontractor | 32000000 | 23100000 | 72.19% | 8900000
Equipment | 14000000 | 10600000 | 75.71% | 3400000
Overheads | 10000000 | 7900000 | 79% | 2100000
TOTAL | 160000000 | 122600000 | 76.62% | 37400000
Earned Value Analysis (EVM)
Standard project-controls metrics. EV = BAC × % complete; CPI = EV / AC; EAC = BAC / CPI.
BAC — Budget at Completion | 160000000 | Total project budget
% Complete (physical) | 75% | Work actually done
EV — Earned Value | 120000000 | Budgeted cost of work performed
AC — Actual Cost | 122600000 | Actual cost incurred to date
CV — Cost Variance (EV − AC) | -2600000 | Positive = under budget
CPI — Cost Performance Index | 0.97879 | EV / AC; >1 = efficient
EAC — Estimate at Completion | 163466666.6667 | BAC / CPI
VAC — Variance at Completion | -3466666.6667 | BAC − EAC

## RA_Bills
Running Account (RA) Bill Status
Bills raised to client — certified, retention, received, pending.
RA Bill No. | Date | Gross Work Value (₹) | Amount Certified (₹) | Retention @5% (₹) | Amount Received (₹) | Pending Receivable (₹) | Excess Received (₹)
RA-01 | May-24 | 12500000 | 12200000 | 610000 | 11200000 | 390000 | 0
RA-02 | Jul-24 | 14800000 | 14500000 | 725000 | 13400000 | 375000 | 0
RA-03 | Sep-24 | 16200000 | 15900000 | 795000 | 14600000 | 505000 | 0
RA-04 | Nov-24 | 15100000 | 14800000 | 740000 | 13600000 | 460000 | 0
RA-05 | Jan-25 | 17400000 | 17000000 | 850000 | 15700000 | 450000 | 0
RA-06 | Mar-25 | 13900000 | 13600000 | 680000 | 12300000 | 620000 | 0
RA-07 | May-25 | 15600000 | 15200000 | 760000 | 13900000 | 540000 | 0
RA-08 | Jul-25 | 14200000 | 13900000 | 695000 | 11800000 | 1405000 | 0
RA-09 | Sep-25 | 11800000 | 11500000 | 575000 | 7600000 | 3325000 | 0
TOTAL |  | 131500000 | 128600000 | 6430000 | 114100000 | 8070000 | 0

## Subcontractors
Subcontractor Status
Subcontractor | Work Package | Order Value (₹) | Billed to Date (₹) | Paid (₹) | Balance Payable (₹) | % Billed
Sri Sai Enterprises | Piling & Foundation | 8500000 | 8500000 | 8100000 | 400000 | 100%
Deccan Steel Works | Structural Steel | 9200000 | 7400000 | 6900000 | 500000 | 80.43%
Kaveri Electricals | Electrical & Wiring | 4800000 | 3100000 | 2700000 | 400000 | 64.58%
Nandi Plumbing Co. | Plumbing & Sanitary | 3600000 | 2500000 | 2200000 | 300000 | 69.44%
Prism Interiors | Finishing & Interiors | 5900000 | 1600000 | 1300000 | 300000 | 27.12%
TOTAL |  | 32000000 | 23100000 | 21200000 | 1900000 | 72.19%

## Manpower
Project-Specific Manpower & Work-Time Costing
Direct site labour (headcount × days × rate) plus agency/contract labour. Ties to Labour actual in Project_Data.
Role / Trade | Headcount | Days Deployed | Rate (₹/day) | Labour Cost (₹)
Project Manager | 1 | 540 | 4500 | 2430000
Site Engineers | 3 | 520 | 2600 | 4056000
Supervisors | 4 | 510 | 1800 | 3672000
Masons | 13 | 405 | 850 | 4475250
Bar Benders / Steel Fixers | 8 | 395 | 900 | 2844000
Carpenters / Shuttering | 10 | 390 | 880 | 3432000
Electricians | 5 | 265 | 950 | 1258750
Plumbers | 4 | 245 | 920 | 901600
Helpers / Unskilled | 28 | 410 | 520 | 5969600
Agency / Contract Labour |  |  |  | 1760800
TOTAL LABOUR | 76 |  |  | 30800000
Reconciliation Check
Labour actual (Project_Data) |  |  |  | 30800000
Total labour (this sheet) |  |  |  | 30800000
Difference |  |  |  | 0

## Materials
Material Consumption & Purchase Price Variance
Material Consumption (Budget Qty vs Actual)
Material | Unit | Budget Qty | Actual Qty (to date) | Qty Variance | Status
Cement | Bags | 42000 | 33200 | 8800 | Within Budget
Steel (TMT) | MT | 1350 | 1058 | 292 | Within Budget
Sand | CFT | 210000 | 168500 | 41500 | Within Budget
Aggregate (20mm) | CFT | 185000 | 146200 | 38800 | Within Budget
Bricks | Nos | 620000 | 498000 | 122000 | Within Budget
Purchase Price Variance — Cement & Steel
PPV = (Standard Rate − Actual Rate) × Actual Qty. Positive = favourable, negative = adverse.
Material | Unit | Std Rate (₹) | Actual Rate (₹) | Actual Qty | Rate Diff (₹) | Purchase Price Variance (₹) | Result
Cement | Bag | 380 | 402 | 33200 | -22 | -730400 | Adverse
Steel (TMT) | kg | 62 | 58 | 1058000 | 4 | 4232000 | Favourable
TOTAL PPV | [5 empty] | 3501600 | Favourable

## Cashflow
Project Cash Flow — Inflow vs Outflow
Inflow = receipts from RA bills. Outflow = payments (material, labour, subcontractor).
Month | Inflow (₹) | Outflow (₹) | Net (₹) | Cumulative Net (₹)
May-24 | 11200000 | 9500000 | 1700000 | 1700000
Jul-24 | 13400000 | 12800000 | 600000 | 2300000
Sep-24 | 14600000 | 14600000 | 0 | 2300000
Nov-24 | 13600000 | 13900000 | -300000 | 2000000
Jan-25 | 15700000 | 15200000 | 500000 | 2500000
Mar-25 | 12300000 | 14100000 | -1800000 | 700000
May-25 | 13900000 | 13700000 | 200000 | 900000
Jul-25 | 11800000 | 13400000 | -1600000 | -700000
Sep-25 | 7600000 | 11200000 | -3600000 | -4300000
TOTAL | 114100000 | 118400000 | -4300000
Accrued Cost vs Cash Outflow — Reconciliation
Accounting (accrued) cost and cash paid differ by movement in payables/accruals.
Accrued Cost to Date (P&L, Project_Data) |  | 122600000
Total Cash Outflow (this sheet) |  | 118400000
Difference = Closing Payables / Accruals |  | 4200000

## Milestones
Milestone / Schedule Tracker
Stage | Planned % | Actual % | Variance (pts) | Status
Site Prep & Excavation | 100% | 100% | 0 | On Track
Foundation & Piling | 100% | 100% | 0 | On Track
Structural Frame | 95% | 92% | -3 | Behind
Masonry & Blockwork | 85% | 80% | -5 | Behind
MEP (Elec/Plumb) | 70% | 62% | -8 | Behind
Plastering & Flooring | 55% | 48% | -7 | Behind
Finishing & Interiors | 30% | 22% | -8 | Behind
External & Handover | 10% | 5% | -5 | Behind